A Sprint is a fixed period or duration in which a team works to complete a set of tasks.

An Epic is a big task or project that is too large to complete in one sprint. It is broken down into smaller tasks (stories) that can be completed over multiple sprints.

A Story is a small task. It is part of an Epic.

A Story Point is a number that represents how much effort a story takes to complete (usually in the form of Fibonacci series):

- 1 = Very Easy task

- 2 = Normal task

- 3 = Moderate task

- 5 = Difficult task

Sprint 1

Catalog Item Setup (Epic 1)

- Creating the Laptop Request Catalog Item under Hardware Category (USN1) — 2

- Adding Laptop Model Variable (USN2) — 1

- Adding Justification Variable (USN3) — 1

- Adding Additional Accessories Checkbox Variable (USN4) — 2

- Adding Accessories Details Variable with UI Policy (USN5) — 3

Total Story Points in Sprint 1 = 2+1+1+2+3 = 9

Sprint 2

UI Action & Deployment (Epic 2)

- Creating Reset Form UI Catalog Action (USN6) — 3

- Creating Update Set "Laptop Request Project" (USN7) — 2

- Marking Update Set Complete and Exporting as XML (USN8) — 2

- Importing XML into Target Instance dev324774 and Previewing (USN9) — 3

- Committing Update Set on Target Instance (USN10) — 3

Total Story Points in Sprint 2 = 3+2+2+3+3 = 13

Total Story Points

Sprint 1 = 9

Sprint 2 = 13

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points = 9 + 13 = 22

No. of Sprints = 2

Velocity = 22 / 2 = 11 Story Points per Sprint

Your team's velocity is 11 Story Points per Sprint.